## Intern_Tracking
Batch | 53
Project | T-Eduone (T-Interview)
Mentor | Lê Văn Hiếu
Intern(s) | Hồ Sỹ Mạnh Hùng | [7 empty] | Not Start |  | On-going |  | On-hold |  | Complete
Phase | Task | Input | Output | Owner (Student name) | Start date | Target date | Actual duration | Remark | Progress/Status
[9 empty] | WEEK 1 (17/08 - 21/08) |  |  |  |  | WEEK 2 (24/08 - 28/08) |  |  |  |  | WEEK 3 (31/08 - 04/09) |  |  |  |  | WEEK 4 (07/09 - 11/09) |  |  |  |  | WEEK 5 (14/09 - 18/09) |  |  |  |  | WEEK 6 (21/09 - 25/09) |  |  |  |  | WEEK 7 (28/09 - 02/10) |  |  |  |  | WEEK 8 (05/10 - 09/10) |  |  |  |  | WEEK 9 (12/10 - 16/10) |  |  |  |  | WEEK 10 (19/10 - 23/10)
[9 empty] | 17/08 | 18/08 | 19/08 | 20/08 | 21/08 | 24/08* | 25/08 | 26/08 | 27/08 | 28/08 | 31/08 | 01/09 | 02/09 | 03/09 | 04/09 | 07/09 | 08/09 | 09/09 | 10/09* | 11/09 | 14/09 | 15/09 | 16/09 | 17/09* | 18/09 | 21/09 | 22/09 | 23/09 | 24/09* | 25/09 | 28/09 | 29/09 | 30/09 | 01/10* | 02/10 | 05/10 | 06/10 | 07/10 | 08/10* | 09/10 | 12/10 | 13/10 | 14/10 | 15/10* | 16/10 | 19/10 | 20/10 | 21/10 | 22/10* | 23/10
1 | 1. UI Comparison Matrix & Accessibility Audit (WCAG 2.0 AA): - Mapped UI comparison matrix across portals - Typography audit & Executive summary - Accessibility audit using axe DevTools & Lighthouse | Portal interfaces, WCAG 2.0 AA checklist | - UI Comparison Matrix across portals - UI Audit Report & WCAG 2.0 AA Gap List - Typography audit documentation | Hồ Sỹ Mạnh Hùng | 8/17/2026 | 8/21/2026 | 5 days | Completed on schedule
| 2. UI Guidelines, Design Tokens & Front-end Snippets: - Secondary color system audit & token mappings - Front-end code snippets following WCAG standards - Team progress report meeting | Design specs, UI Audit Report | - Secondary color system audit and token mappings - Approved front-end code snippets - Action items from team meeting | Hồ Sỹ Mạnh Hùng | 8/19/2026 | 8/21/2026 | 3 days | Completed Week 1 milestones
| 3. Business Analysis & Environment Setup for T-Interview: - BA requirement breakdown (UI, Backend, AI modules) - Antigravity IDE setup & AI Agent structure (frontend-mfp) - Compiling initial 3-week internship report for university | SRS, T-Interview scope, Antigravity IDE | - Module breakdown document (UI/Backend/AI) - Antigravity AI Agent configured - Drafted internship report for university | Hồ Sỹ Mạnh Hùng | 8/25/2026 | 8/28/2026 | 4 days | Nghỉ phép 24/08 | [5 empty] | OFF
2 | 4. Issue #3 - Interview Data Model Implementation: - Restructured database schema - Reusable module migration from SaleCoach to Interview project - Implemented physical database storage matching data model | SaleCoach codebase, Data model spec | - Standardized Interview database schema - Physical DB storage structure & migrations - Reusable SaleCoach modules integrated | Hồ Sỹ Mạnh Hùng | 8/28/2026 | 9/03/2026 | 5 days | Completed & verified
| 5. Bug Fixes & UI Refinements for EduOne Portal: - Resolved UI defects and styling issues on EduOne portal - Pushed code and created Merge Request (MR) | EduOne bug backlog | - Fixed UI defects on EduOne - Merge Request submitted for code review | Hồ Sỹ Mạnh Hùng | 9/02/2026 | 9/03/2026 | 2 days | MR submitted
| 6. Issue #14 - Create/Edit/Delete Interview Domain: - CRUD interface & APIs for Domain (Name, Description, Language) - Soft-delete constraint: set to 'deprecated' with warnings | Domain requirement spec | - CRUD APIs and UI for Interview Domain - Deprecated status logic protecting referenced data | Hồ Sỹ Mạnh Hùng | 9/04/2026 | 9/08/2026 | 3 days | Completed with unit tests
| 7. Development Infrastructure & Docker Environment Setup: - VS Code Flatpak terminal & host OS permission resolution - Docker Engine & Docker Compose deployment - NestJS backend (3000), React Vite (5173), SSO Admin login | Docker Compose configs, SSO configs | - Stable containerized local infrastructure - Swagger docs active at /docs - SSO login working without 401 errors | Hồ Sỹ Mạnh Hùng | 9/07/2026 | 9/08/2026 | 2 days | Fixed TypeORM metadata error
| 8. Issue #6 - Campaign Management (Schema & CRUD): - TypeORM schema, soft-delete, aggregate queries (candidate count) - Status constraints (Open/Closed), Postman API testing - Frontend table, debounced search, status filter | Campaign user stories, UI mockup | - Full Campaign CRUD APIs with soft-delete - Filterable Campaign management UI - Business rule blocking sessions on closed campaigns | Hồ Sỹ Mạnh Hùng | 9/07/2026 | 9/11/2026 | 4 days | Nghỉ học trường 10/09 | [18 empty] | OFF
3 | 9. Issue #23 & Scenario Management Drag-and-Drop: - Drag-and-drop ordering for Stages & Signals in Scenarios - Merged demo_v1_ui into branch, resolved merge conflicts - Fixed infinite render in AdminScenariosDraft.tsx & added i18n | Scenario wireframes, branch demo_v1_ui | - Interactive drag-and-drop scenario builder - Cleaned code without infinite re-renders - i18n translation keys integrated | Hồ Sỹ Mạnh Hùng | 9/11/2026 | 9/15/2026 | 3 days | Completed & verified
| 10. Interview Digitization & Workflow Modernization: - Project meeting on candidate profiling & avatar interview flows - Refined and customized system UI components - Updated DB schema & migrations to support new business flows | Stakeholder meeting notes | - Updated T-Interview DB schema and migrations - Tailored UI components for candidate profiling | Hồ Sỹ Mạnh Hùng | 9/16/2026 | 9/18/2026 | 2 days | Nghỉ học trường 17/09 | [23 empty] | OFF
| 11. Scenario Menu Implementation & AI Interview Flow Testing: - Designed operational workflow of Scenarios in system - Implemented Scenario menu with complete field definitions - Updated TMA logo, fixed Position & Project API integrations | Scenario operational workflow | - Completed Scenario menu UI & data binding - TMA branding applied to AI Interview UI - End-to-end verified interview flow | Hồ Sỹ Mạnh Hùng | 9/21/2026 | 9/23/2026 | 3 days | Nghỉ học trường 24/09 | [28 empty] | OFF
| 12. Portal Redesign - Auth Pages (Login/Register) & Scenario: - Redesigned and updated UI for Login and Register pages - Redesigned layout and components for Scenario page | Updated Figma design guidelines | - Modern Login & Register user interfaces - Responsive Scenario management layout | Hồ Sỹ Mạnh Hùng | 9/25/2026 | 9/28/2026 | 2 days | Completed UI overhaul
4 | 13. Issue #101 - Session Report UI & Evaluation Flow: - Redesigned layout with question navigation and sticky review panel - Transcript filtering to isolate question-specific dialogue turns - Bilingual translations (i18n) for evaluation metrics | Evaluation flow specs, rubric metrics | - Interactive Session Report interface - Turn-by-turn question dialog filtering - Bilingual evaluation metrics | Hồ Sỹ Mạnh Hùng | 9/29/2026 | 9/30/2026 | 2 days | Verified end-to-end
| 14. Issue #102 - Export Session Report to PDF: - Built PDF download feature for completed evaluated sessions - Role-based permissions & display constraints - Added dialogue transcript & Final Rubric page into exported PDF | PDF export requirement, report layout | - Working PDF export module with permission gates - Formatted PDF containing full transcript & rubric | Hồ Sỹ Mạnh Hùng | 9/30/2026 | 10/12/2026 | 4 days | Resolved MR comments 12/10 (Nghỉ 01/10) | [33 empty] | OFF
| 15. Audio Streaming & Port Host Integration: - Implemented audio port host configuration & streaming connections - Verified audio transmission latency between client and backend - End-to-end audio communication testing for interview sessions | Audio server config, WebSocket protocol | - Stable audio streaming pipeline - Verified low-latency transmission for interview audio | Hồ Sỹ Mạnh Hùng | 10/05/2026 | 10/06/2026 | 2 days | Audio pipeline verified
| 16. Issue #92 - Voice Cloning Architecture & Avatar Integration: - Researched voice cloning models & audio sampling pipeline - Implemented service connection & voice synthesis quality testing - Created Merge Request (MR) to dev branch for Mentor review | Voice cloning AI models, audio service | - Completed voice cloning integration - High quality voice synthesis for AI interviewer - Merge Request submitted to branch dev | Hồ Sỹ Mạnh Hùng | 10/06/2026 | 10/09/2026 | 3 days | Nghỉ học trường 08/10 | [38 empty] | OFF
5 | 17. T-Avatar Module Foundation & Service Integrations: - Researched architecture, requirements, and finalized task breakdown with the team - Developed initial foundational setup, core components, and service integrations - Resolved and fixed issues from recent commits; verified communication flows with interview system | T-Avatar architecture design, voice cloning pipeline, interview system API specs | - Foundational components and service integrations for T-Avatar module - Verified communication flow between T-Avatar and interview system | Hồ Sỹ Mạnh Hùng | 10/12/2026 | 10/14/2026 | 3 days | Nghỉ học trường 15/10 | [43 empty] | OFF
| 18. Issue #106 - Core Components & Business Logic Implementation: - Implemented core components and business logic according to task specifications - Handled data flow integration and verified baseline functionalities with related modules - Created Merge Request (MR) on GitLab, addressed and resolved review comments | Issue #106 specifications, related module interfaces, GitLab review feedback | - Finalized implementation and verified integration for issue #106 - GitLab Merge Request (MR) submitted, reviewed, and merged | Hồ Sỹ Mạnh Hùng | 10/16/2026 | 10/21/2026 | 3 days | MR submitted & resolved comments
| 19. T-Avatar Progress Tracking & End-to-End Interviewer Flow Testing: - Implemented progress tracking feature, flow, and UI updates for T-Avatar module - Conducted end-to-end (E2E) testing for interviewer flow to ensure cross-feature stability - Verified edge cases, addressed newly identified bugs, and ensured code quality standards | Avatar progress tracking specs, interviewer flow test cases, UI designs | - Working progress tracking flow & refined UI for T-Avatar - Verified end-to-end interview flow with edge cases tested and resolved | Hồ Sỹ Mạnh Hùng | 10/19/2026 | 10/23/2026 | 4 days | Nghỉ học trường 22/10 | [48 empty] | OFF