## Project plan
Project Plan
Project Information
Batch
Project name | T-Eduone
Project Leader | Dat Le
Mentor | Hieu Le
Project description | T-Eduone is an education center management platform (EduOne) composed of multiple portals: CRM for center staff, LMS for e-learning students, an online Examination system (Exams), a Customer Portal for parents, an aggregator Portal, and EduOne Play (interactive quiz). The frontend is built with React + TypeScript on an Nx workspace using Module Federation, sharing the shared-ui / shared-hooks / shared-pages libraries; the backend is a set of NestJS microservices with PostgreSQL. Because the portals were developed at different points in time, their user interfaces are currently inconsistent in color, typography, spacing and component behaviour.
Project Scope | The intern (React + .NET background) joins the project as a Frontend Developer and focuses 100% on frontend work. The main goal is to standardize and unify the user interface (UI consistency) across all EduOne portals: 1) Audit and compare the current UI of every portal (CRM, LMS, Exams, Customer, Portal) and produce a common UI guideline. 2) Build a design token set (color, typography, spacing, radius, shadow) and standardize the shared component library libs/shared-ui inside the frontend-mfp Nx workspace. 3) Roll the standardized components out to each portal: unify layout, forms, data tables, notifications and the loading / empty / error states; align responsive behaviour and basic accessibility. 4) Write unit tests (Vitest) with at least 80% coverage for shared components; follow the project coding convention and code review process. Out of scope: API / backend development, DevOps and infrastructure, new UX design from scratch, third-party integrations.
Key Deliverables
# | Deliverable | Start date | Target date | Input | Output | Remark
1 | D1 - UI Audit & Design Tokens: audit all portals, produce a common UI guideline and build the design token set (color, typography, spacing, radius, shadow, light/dark theme) in libs/shared-ui. | 03/08/2026 | 31/08/2026 | Onboarding documents, edu-crm repository, CLAUDE.md, access to the dev environment of all portals, screenshots / documents of the current UI, brand guideline (if available). | UI audit report (comparison matrix of differences across portals) and UI guideline; design token set merged into libs/shared-ui; pull request merged into the dev-eduone branch; theme demo on one sample portal. | Month 1 - Ramp-up. Pair programming with mentor twice a week; guideline must be approved by the Project Leader before implementation.
2 | D2 - Shared component library standardization: refactor the existing libs/shared-ui components to the design tokens and add the missing ones (Dialog, Pagination, Badge, EmptyState, Breadcrumb, Skeleton). | 01/09/2026 | 30/09/2026 | UI guideline and design tokens from D1; current libs/shared-ui source (button, input, select, card, table, data-table, toast, dropdown-menu, avatar...); list of components duplicated inside each application. | Standardized libs/shared-ui: consistent variant / size API, no hard-coded colors or sizes; new components added; Vitest unit tests with coverage >= 80%; component usage documentation. | Month 2 - Main technical focus. No breaking changes for the applications currently consuming the library, or a migration guide must be provided.
3 | D3 - UI rollout across portals: standardize the application shell (header, sidebar, app switcher, breadcrumb, loading / 404 / 403 pages) and replace local components with shared-ui in LMS, Exams, Customer, Portal and CRM. | 01/10/2026 | 30/10/2026 | Standardized libs/shared-ui from D2; UI guideline; prioritized screen list approved by the Leader / Mentor; dev environment of each portal. | All portals share a consistent interface following the guideline; duplicated CSS and components removed; responsive behaviour and basic accessibility aligned; pull requests reviewed and merged; handover documentation and an end-to-end demo closing the internship. | Month 3 - Works independently, mentor only reviews. UI regression check required before merging each portal.
Project Schedule
# | Task name | Start date | Target date | Duration (days) | Remark
Deliverable #1
1 | Set up the frontend environment: Node/npm, the frontend-mfp Nx workspace and the standalone CRM; run all portals (crm, lms, exams, customer, portal) locally; get familiar with Module Federation, the Git flow and the code review process. | 03/08/2026 | 07/08/2026 | 5 | Mentor assists with the setup on day one.
2 | UI audit: review and build a comparison matrix of the UI differences across portals (colors, typography, spacing, buttons, forms, data tables, notifications, empty / error states), with supporting screenshots. | 10/08/2026 | 18/08/2026 | 7 | Output: UI audit report; reviewed with the Leader.
3 | Design and implement the shared design token set in libs/shared-ui (color palette, typography scale, spacing, radius, shadow, z-index) and support light / dark themes across all portals. | 19/08/2026 | 27/08/2026 | 7 | Main task of month 1.
4 | Write the UI guideline document, demo the theme on one sample portal, address code review comments and merge into the dev-eduone branch. | 28/08/2026 | 31/08/2026 | 2 | D1 acceptance.
Deliverable #2
1 | Refactor the foundation components to the design tokens: Button, Input, Label, Select, Switch, Card - unify the variant / size API and remove hard-coded colors and sizes. | 01/09/2026 | 08/09/2026 | 6 | No breaking changes for the applications in use.
2 | Refactor the data and feedback components: Table / DataTable, SearchInput, DropdownMenu, Toast / Toaster, Avatar, FileDropzone - unify the loading / empty / error states. | 09/09/2026 | 16/09/2026 | 6 | Cross-checked against the D1 UI guideline.
3 | Add the missing components to libs/shared-ui: Dialog / Modal, Pagination, Badge / Tag, EmptyState, Breadcrumb, Skeleton - replacing the versions duplicated in each application. | 17/09/2026 | 25/09/2026 | 7 | Main task of month 2.
4 | Write Vitest unit tests for shared-ui (coverage >= 80%), write the component usage documentation, address code review comments and release the new version to the applications. | 28/09/2026 | 30/09/2026 | 3 | D2 acceptance.
Deliverable #3
1 | Standardize the shared application shell across portals: header, sidebar, app switcher, breadcrumb and the loading / 404 / 403 pages (libs/shared-ui + shared-pages). | 01/10/2026 | 08/10/2026 | 6 | Intern works proactively, mentor reviews.
2 | Roll shared-ui out to LMS and Exams: replace local components, remove duplicated CSS and verify every screen against the UI guideline. | 09/10/2026 | 19/10/2026 | 7 | Screens prioritized by the Leader.
3 | Roll shared-ui out to the Customer Portal, Portal and CRM-MFP; align responsive behaviour (mobile / tablet) and basic accessibility (contrast, focus state, aria-label). | 20/10/2026 | 27/10/2026 | 6 | Main task of month 3.
4 | Run a UI regression check across all portals, write the handover documentation, deliver the end-to-end demo and the internship closing assessment. | 28/10/2026 | 30/10/2026 | 3 | D3 acceptance and final evaluation.