## Intern_Tracking
Batch | 53
Project | Teledeaf
Mentor | Nguyễn Ngọc Kiệm
Intern(s) | Võ Văn Thiệt | [7 empty] | Not Start |  | On-going |  | On-hold |  | Complete
Phase | Task | Input | Output | Owner (Student name) | Start date | Target date | Actual duration | Remark | Progress/Status
[9 empty] | WEEK 1 (17/08 - 21/08) |  |  |  |  | WEEK 2 (24/08 - 28/08) |  |  |  |  | WEEK 3 (31/08 - 04/09) |  |  |  |  | WEEK 4 (07/09 - 11/09) |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8
[9 empty] | 17/08 | 18/08 | 19/08 | 20/08 | 21/08 | 24/08 | 25/08 | 26/08 | 27/08 | 28/08 | 31/08 | 01/09 | 02/09 | 03/09 | 04/09 | 07/09 | 08/09 | 09/09 | 10/09 | 11/09 | 14/09 | 15/09 | 16/09 | 17/09 | 18/09 | 21/09 | 22/09 | 23/09 | 24/09 | 25/09 | 28/09 | 29/09 | 30/09 | 01/10 | 02/10 | 05/10 | 06/10 | 07/10 | 08/10 | 09/10
1 | 1. Set up PC, Network, Email, Teams, Report, Android Studio |  | Set up PC, Network, Email, Teams, Report,, Android Studio | Thiệt Võ | 8/17/2026 | 8/19/2026 | 2 day
| 2.Self-study Security Awareness online course |  | Pass the online test | Thiệt Võ | 8/20/2026 | 8/20/2026 | 1 day
| Kotlin Language: - Basics - Classes and Objects - Functions and Lambdas - Kotlin Coroutine |  | Understanding Kotlin language | Thiệt Võ | 8/21/2026 | 8/26/2026 | 4 days
| Android Basic: - Lifecycle - UI Layouts - UI Lists |  | - Understand how Android manages Activities and how to handle lifecycle events properly. - Build responsive and adaptive user interfaces using XML layouts. - Display and interact with dynamic lists. | Thiệt Võ | 8/27/2026 | 8/28/2026 | 2 days
| - REST API and Parse data - Dagger Hilt |  | - Connect your app to a RESTful API and parse JSON responses. - Use dependency injection to manage object creation and lifecycles. | Thiệt Võ | 8/31/2026 | 8/31/2026 | 1 days
| - Broadcast receiver - Service |  | - React to system-wide or app-wide events. - Run background tasks with proper lifecycle management. | Thiệt Võ | 9/3/2026 | 9/4/2026 | 2 days
| - Room Database & SQLite - Local Data Persistence |  | - Implement Room DAO, Entity, Database - Cache offline data efficiently | Thiệt Võ | 9/7/2026 | 9/9/2026 | 3 days
2 | Project Teledeaf - Architecture & Analysis: - Requirement Analysis - MVVM Architecture & Clean Architecture | SRS Document | - Architecture diagram - Base code & module structure setup | Thiệt Võ | 9/10/2026 | 9/15/2026 | 4 days
| Project Teledeaf - Core Feature Development: - Real-time Audio/Video processing - Deaf-assistance UI & Accessibility | Figma design, API specs | - Implement core feature screens - Integrate backend API and WebSockets | Thiệt Võ | 9/16/2026 | 9/25/2026 | 8 days
| Testing, Code Review & Final Report: - Unit Test & Integration Test - Bug fixing & Mentor code review - Final Internship Report & Presentation | Working APK | - Final Report Slides & Document - Stable release build - Completed internship evaluation | Thiệt Võ | 9/28/2026 | 10/09/2026 | 10 days